## Relatório
|  |  | PROGRESS MONITORING REPORT | [18 empty] | Inter-American Development Bank - IDB
|  |  | JA-L1046 - Public Sector Efficiency Program | [18 empty] | Office of Strategic Planning and Development Effectiveness
|  |  | 2013 1º period closed in (30-Sep-2013) | [18 empty] | Last Update: 18/10/2013
Basic Data
Available Funds (US$) | [11 empty] | Dates
[6 empty] | Loan | [5 empty] | Date of Approval: | [12 empty] | Original Disbursement Expiration Date:
Current Approved Amount | [11 empty] | Date of Signature: | [12 empty] | Current Disbursement Expiration Date:
Disbursed Amount to Date | [11 empty] | Date of Contract Effectiveness: | [12 empty] | Cumulative Extension (months):
% Disbursed | [11 empty] | Date of Eligibility: | [12 empty] | Special Extensions (months):
Balance | [11 empty] | Date of First Disbursement :
Basic Data
Loan Number(s):
Executing Agency (EA): |  |  |  | PLANNING INSTITUTE OF JAMAICA
Team Leader: |  |  |  | von Horoch, Jorge Luis
Operation Type: |  |  |  | INV - Investment | [13 empty] | Related Operation(s): | [9 empty] | RG-P1509
Operation Subtype: |  |  |  | ESP - Specific Investment Operation
Lending Instrument: |  |  |  | Investment
Borrower:
Sector:
Stage: |  |  |  | Profile Ready | [13 empty] | Project Status:
IDB-8 Lending Targets | [17 empty] | Source
( ) Poverty Targeted Investments (PTI) | [17 empty] | Original IDB:
( ) Social Equity Enhancing (SEQ) | [17 empty] | Current IDB:
[18 empty] | Pari-passu: | [18 empty] | 53
IDB-9 Lending Targets | [17 empty] | Co-Financing/Country: | [18 empty] | 12650000
Amortization Period (months):
( ) Small and vulnerable countries
( ) Poverty decrease and equity increase | [17 empty] | Total Project Cost
( ) Climate change, sustainable energy and environmental sustainablity
( ) Regional cooperation and integration | [17 empty] | Original Estimate: | [18 empty] | 12650000
Project Environmental and Social Impact Category | [17 empty] | Reformulation
Project Environmental and Social Impact Category: | [13 empty] | None |  |  |  | ( ) Was the objective(s) of this project reformulated?
Date of Board Approval:
Evaluation (to be imported from DEM)
Economic Performance
( ) Reflexive (Before/After)
( ) Quasi Experimental | [17 empty] | ( ) Cost Effectiveness
( ) Experimental | [17 empty] | ( ) Economic Rate of Return (ERR)
Basic Data
Project Objective:
The general objective of the program is to improve the efficiency of the Jamaican public sector.
Impacts
Impact: |  | Improvement of the efficiency of the Jamaican public sector.
Indicator | [25 empty] | Unit of Measure | [5 empty] | Baseline |  |  |  | Baseline Year |  |  | End of project
Central Government Wage bill as a percentage of Gross Domestic Product | [25 empty] | Percentage (%) | [5 empty] | 10 |  |  |  | 2013 |  | P | 9
A
Central Government Wage Bill as a percentage of non-debt expenditure. | [25 empty] | Percentage (%) | [5 empty] | 53 |  |  |  | 2013 |  | P | 44
A
Verification means and impact indicators observations
Impact: |  | Improvement of the efficiency of the Jamaican public sector.
Indicator | [8 empty] | Unit of Measure |  |  |  |  | Means of verification | [12 empty] | Comments
Central Government Wage bill as a percentage of Gross Domestic Product | [8 empty] | Percentage (%) |  |  |  |  | MOFP | [12 empty] | Baseline (10.7), Baseline year (2013), EOP Targe (9.0) - Remarks- GOJ?s medium term strategy described in the Memorandum of Economic and Financial Policies
Central Government Wage Bill as a percentage of non-debt expenditure. | [8 empty] | Percentage (%) |  |  |  |  | MOFP | [12 empty] | Baseline (53.1), Baseline year (2013), EOP Target (44.0)
Outcomes
Outcome: |  | 1. Enhanced HRM contributing to maintaining a fiscally sustainable wage bill
Indicator | [25 empty] | Unit of Measure | [5 empty] | Baseline |  |  |  | Baseline Year |  |  | End of project
Percentage of public sector employees managed through a centralized and integrated human capital management system integrated with payroll | [25 empty] | Percent | [9 empty] | 2013 |  | P | 100
A
PEFA PI- 18. Effectiveness of payroll control | [25 empty] | Score | [9 empty] | 2012 |  | P
A
Outcome: |  | 2. Efficiency gains in public sector operations and a more cost-effective delivery of public services
Indicator | [25 empty] | Unit of Measure | [5 empty] | Baseline |  |  |  | Baseline Year |  |  | End of project
Number of days for getting electricity | [25 empty] | Days | [5 empty] | 96 |  |  |  | 2013 |  | P | 76
A
Number of days to register a business | [25 empty] | Days | [5 empty] | 7 |  |  |  | 2013 |  | P | 1
A
On line service Index | [25 empty] | Score | [5 empty] | 307 |  |  |  | 2012 |  | P | 360
A
Percentage of public sector employees with access to HR Shared Corporate Services (cumulative) | [25 empty] | Percentage | [9 empty] | 2013 |  | P | 60
A
Outcome: |  | 3. Enhanced control and accountability of public resources
Indicator | [25 empty] | Unit of Measure | [5 empty] | Baseline |  |  |  | Baseline Year |  |  | End of project
Number of Information Systems Audit Reports produced | [25 empty] | # | [5 empty] | 2 |  |  |  | 2012 |  | P | 6
A
PEFA PI-21. Effectiveness of internal audit | [25 empty] | Score | [9 empty] | 2012 |  | P
A
PEFA PI- 19. Competition, VfM and controls in procurement. | [25 empty] | Score | [9 empty] | 2013 |  | P
A
PEFA PI -27. Legislative scrutiny of the annual budget law | [25 empty] | Score | [9 empty] | 2013 |  | P
A
Verification means and outcome indicators observations
Outcome: |  | 1. Enhanced HRM contributing to maintaining a fiscally sustainable wage bill
Indicator | [8 empty] | Unit of Measure |  |  |  |  | Means of verification | [12 empty] | Comments
Percentage of public sector employees managed through a centralized and integrated human capital management system integrated with payroll | [8 empty] | Percent |  |  |  |  | MOFP
PEFA PI- 18. Effectiveness of payroll control | [8 empty] | Score |  |  |  |  | PEFA | [12 empty] | Unit of Measure (PEFA scores: A, B, C or D (- or +)). Baseline: D+, EOP Target: C
Outcome: |  | 2. Efficiency gains in public sector operations and a more cost-effective delivery of public services
Indicator | [8 empty] | Unit of Measure |  |  |  |  | Means of verification | [12 empty] | Comments
Number of days for getting electricity | [8 empty] | Days |  |  |  |  | Doing Business Report (WB)
Number of days to register a business | [8 empty] | Days |  |  |  |  | Doing Business Report (WB)
On line service Index | [8 empty] | Score |  |  |  |  | The UN Global E-government Survey | [12 empty] | Score ranges from 0 to 1 -highest; Unit of Measure=Score, Baseline= 0.307, EOP: 0.360
Percentage of public sector employees with access to HR Shared Corporate Services (cumulative) | [8 empty] | Percentage |  |  |  |  | Cabinet Office of Government of Jamailca
Outcome: |  | 3. Enhanced control and accountability of public resources
Indicator | [8 empty] | Unit of Measure |  |  |  |  | Means of verification | [12 empty] | Comments
Number of Information Systems Audit Reports produced | [8 empty] | # |  |  |  |  | AGD
PEFA PI-21. Effectiveness of internal audit | [8 empty] | Score |  |  |  |  | PEFA | [12 empty] | PEFA scores: A, B, C or D (- or +). Baseline: D+, EOP Target: C
PEFA PI- 19. Competition, VfM and controls in procurement. | [8 empty] | Score |  |  |  |  | PEFA | [12 empty] | PEFA scores: A, B, C or D (- or +). Baseline: C+, EOP Target: B
PEFA PI -27. Legislative scrutiny of the annual budget law | [8 empty] | Score | [17 empty] | PEFA scores: A, B, C or D (- or +). Baseline: D+, EOP Target: C
Outputs
Output |  |  |  |  | Unit of Measure | [7 empty] | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  | 2016 | [6 empty] | 2017 |  |  |  | 2018 |  |  |  | End of project
Component Title: Component 1: Human resources management
HCMS implemented |  |  |  |  | # | [6 empty] | P | [18 empty] | 1 | [7 empty] | 1
A
Workshop on international experiences on workforce planning delivered |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Training activity in HRM policy formulation and oversight for implementation completed |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 |  |  | 1 | [14 empty] | 2
A
Number of HRM Units in MDAs trained to carry out key HRM functions following central policies |  |  |  |  | # | [6 empty] | P | [8 empty] | 10 |  |  | 35 | [6 empty] | 35 |  |  |  | 45 |  |  |  | 125
A
'To-Be' Key HRM processes developed and mapped |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Training on techniques for monitoring overall and institutional-level HRM performance for SHRMD delivered |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Component Title: Component 2: Efficiency gains in public sector operations and a more cost-effective del of pub servs
e-Government strategy completed |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 | [21 empty] | 1
A
ICT norms and standards produced (cumulative) |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 | [21 empty] | 1
A
e-Gov Jamaica training programs delivered (cumulative) |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 |  |  |  | 2 |  |  | 3 | [6 empty] | 2 |  |  |  | 1 |  |  |  | 9
A
GEI business process reengineering completed |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
GEI process automation completed and online applications system in operation |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
GEI training program on the new system delivered (cumulative) |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Online business registration system in operation |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Business registration kiosks in operation (cumulative) |  |  |  |  | # | [6 empty] | P | [11 empty] | 23 | [14 empty] | 23
A
Business registration seminars and workshops delivered (cumulative) |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Communications campaign implemented (cumulative) |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Study Tour completed |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 | [21 empty] | 1
A
HRSSC Operating Model designed |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 | [21 empty] | 1
A
Technical specification designed and available for HRSSC facility, including ICT infrastructure |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
ICT infrastructure to operate HRSSC in operation |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Training to HRSSC agents/workers delivered |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Component Title: Component 3: Control systems and accountability
Auditors trained - in country - for developing/up-dating PA knowledge and skills |  |  |  |  | # | [6 empty] | P |  |  |  |  | 45 | [6 empty] | 45 | [14 empty] | 90
A
Auditors trained  in country and overseas for developing/updating ITA knowledge and skills |  |  |  |  | # | [6 empty] | P |  |  |  |  | 45 | [6 empty] | 45 | [14 empty] | 90
A
ITA manual drafted and disseminated |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Auditors trained overseas completed |  |  |  |  | # | [6 empty] | P | [8 empty] | 3 |  |  | 3 | [6 empty] | 3 |  |  |  | 3 |  |  |  | 12
A
Additional licenses for interrogation software installed |  |  |  |  | # | [6 empty] | P |  |  |  |  | 12 | [21 empty] | 12
A
Professional Development framework for Internal Audit Units (IAU) completed |  |  |  |  | # | [6 empty] | P |  |  |  |  | 1 | [21 empty] | 1
A
Automated internal audit system in operation |  |  |  |  | % of IAU | [6 empty] | P |  |  |  |  | 50 |  |  |  | 50 | [17 empty] | 100
A
Internal Audit Manual updated (unit of measure is 1 manual) |  |  |  |  | Manual | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
IA employees trained |  |  |  |  | # of Auditors | [6 empty] | P | [11 empty] | 240 | [14 empty] | 240
A
Procurement Manual published, including updated bidding documents |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Procurement employees trained under new curricula (MIND) (cumulative) |  |  |  |  | # | [6 empty] | P | [8 empty] | 300 |  |  | 300 | [6 empty] | 300 |  |  |  | 300 |  |  |  | 1200
A
Sensitization and awareness campaign implemented |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 |  |  | 1 | [14 empty] | 2
A
Procurement employees certified (cumulative) |  |  |  |  | # | [6 empty] | P | [8 empty] | 50 |  |  | 50 | [6 empty] | 50 |  |  |  | 50 |  |  |  | 200
A
E-tendering software at MOFP in operation |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Management Accountability Framework designed |  |  |  |  | # | [6 empty] | P | [11 empty] | 1 | [14 empty] | 1
A
Technical Office established and functioning |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 | [17 empty] | 1
A
Training for PAC and PAAC members delivered |  |  |  |  | # | [6 empty] | P | [8 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 4
A
Costs
(US$ 000)
Outputs | [6 empty] | Total Cost US$ |  |  |  |  | 2013 |  |  |  | 2014 |  |  | 2015 |  |  |  | 2016 | [6 empty] | 2017 |  |  |  | 2018 |  |  |  | Progress to Date
Component Title: Component 1: Human resources management
HCMS implemented | [6 empty] | 17579 |  |  |  | P | [18 empty] | 17579
A
Workshop on international experiences on workforce planning delivered | [6 empty] | 50 |  |  |  | P | [7 empty] | 50
A
Training activity in HRM policy formulation and oversight for implementation completed | [6 empty] | 100 |  |  |  | P | [7 empty] | 50 |  |  |  | 50
A
Number of HRM Units in MDAs trained to carry out key HRM functions following central policies | [6 empty] | 500 |  |  |  | P | [7 empty] | 40 |  |  |  | 140 | [6 empty] | 140 |  |  |  | 180
A
'To-Be' Key HRM processes developed and mapped | [6 empty] | 300 |  |  |  | P | [11 empty] | 300
A
Training on techniques for monitoring overall and institutional-level HRM performance for SHRMD delivered | [6 empty] | 50 |  |  |  | P | [11 empty] | 50
A
Component Title: Component 2: Efficiency gains in public sector operations and a more cost-effective del of pub servs
e-Government strategy completed | [6 empty] | 396 |  |  |  | P |  |  |  |  | 396
A
ICT norms and standards produced (cumulative) | [6 empty] | 315 |  |  |  | P |  |  |  |  | 396
A
e-Gov Jamaica training programs delivered (cumulative) | [6 empty] | 889 |  |  |  | P |  |  |  |  | 132 |  |  | 192 |  |  |  | 252 | [6 empty] | 192 |  |  |  | 121
A
GEI business process reengineering completed | [6 empty] | 40 |  |  |  | P | [7 empty] | 40
A
GEI process automation completed and online applications system in operation | [6 empty] | 450 |  |  |  | P | [11 empty] | 450
A
GEI training program on the new system delivered (cumulative) | [6 empty] | 10 |  |  |  | P | [11 empty] | 10
A
Online business registration system in operation | [6 empty] | 228 |  |  |  | P | [7 empty] | 228
A
Business registration kiosks in operation (cumulative) | [6 empty] | 23 |  |  |  | P | [11 empty] | 23
A
Business registration seminars and workshops delivered (cumulative) | [6 empty] | 10 |  |  |  | P | [7 empty] | 10
A
Communications campaign implemented (cumulative) | [6 empty] | 39 |  |  |  | P | [7 empty] | 39
A
Study Tour completed | [6 empty] | 25 |  |  |  | P |  |  |  |  | 25
A
HRSSC Operating Model designed | [6 empty] | 578 |  |  |  | P |  |  |  |  | 578
A
Technical specification designed and available for HRSSC facility, including ICT infrastructure | [6 empty] | 241 |  |  |  | P | [7 empty] | 241
A
ICT infrastructure to operate HRSSC in operation | [6 empty] | 708 |  |  |  | P | [11 empty] | 708
A
Training to HRSSC agents/workers delivered | [6 empty] | 48 |  |  |  | P | [11 empty] | 48
A
Component Title: Component 3: Control systems and accountability
Auditors trained - in country - for developing/up-dating PA knowledge and skills | [6 empty] | 268 |  |  |  | P |  |  |  |  | 136 | [6 empty] | 133
A
Auditors trained  in country and overseas for developing/updating ITA knowledge and skills | [6 empty] | 165 |  |  |  | P |  |  |  |  | 82 | [6 empty] | 82
A
ITA manual drafted and disseminated | [6 empty] | 61 |  |  |  | P | [7 empty] | 61
A
Auditors trained overseas completed | [6 empty] | 96 |  |  |  | P | [7 empty] | 24 |  |  |  | 24 | [6 empty] | 24 |  |  |  | 24
A
Additional licenses for interrogation software installed | [6 empty] | 75 |  |  |  | P |  |  |  |  | 75
A
Professional Development framework for Internal Audit Units (IAU) completed | [6 empty] | 105 |  |  |  | P |  |  |  |  | 105
A
Automated internal audit system in operation | [6 empty] | 805 |  |  |  | P |  |  |  |  | 403 |  |  | 403
A
Internal Audit Manual updated (unit of measure is 1 manual) | [6 empty] | 17 |  |  |  | P | [7 empty] | 17
A
IA employees trained | [6 empty] | 152 |  |  |  | P | [11 empty] | 152
A
Procurement Manual published, including updated bidding documents | [6 empty] | 80 |  |  |  | P | [7 empty] | 80
A
Procurement employees trained under new curricula (MIND) (cumulative) | [6 empty] | 450 |  |  |  | P |  |  |  |  | 140 |  |  | 155 |  |  |  | 55 | [6 empty] | 55 |  |  |  | 45
A
Sensitization and awareness campaign implemented | [6 empty] | 80 |  |  |  | P | [7 empty] | 40 |  |  |  | 40
A
Procurement employees certified (cumulative) | [6 empty] | 650 |  |  |  | P | [7 empty] | 162 |  |  |  | 162 | [6 empty] | 162 |  |  |  | 162
A
E-tendering software at MOFP in operation | [6 empty] | 2160 |  |  |  | P | [11 empty] | 2160
A
Management Accountability Framework designed | [6 empty] | 150 |  |  |  | P | [11 empty] | 150
A
Technical Office established and functioning | [6 empty] | 528 |  |  |  | P | [7 empty] | 528
A
Training for PAC and PAAC members delivered | [6 empty] | 80 |  |  |  | P | [7 empty] | 20 |  |  |  | 20 | [6 empty] | 20 |  |  |  | 20
A
Total | [6 empty] | 28502 |  |  |  | P | 0 |  |  |  | 2468 |  |  | 2381 |  |  |  | 5010 | [6 empty] | 18172 |  |  |  | 552 |  |  |  | 0
[11 empty] | A | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0
Disbursements
- No information available
Outputs: Annual Physical and Financial Progress 2013
[8 empty] | Unit |  | Physical | [11 empty] | Financial
Description | [7 empty] | of Measure |  | Planned |  |  |  |  | Actual |  | Accumulated units |  |  | EOP units |  | Planned | [6 empty] | Actual |  |  |  | Accumulated costs |  |  |  | EOP costs
Component 1: Human resources management
| HCMS implemented | [6 empty] | # | [11 empty] | 1 | [16 empty] | 17578535
| Workshop on international experiences on workforce planning delivered | [6 empty] | # | [11 empty] | 1 | [16 empty] | 50000
| Training activity in HRM policy formulation and oversight for implementation completed | [6 empty] | # | [11 empty] | 2 | [16 empty] | 100000
| Number of HRM Units in MDAs trained to carry out key HRM functions following central policies | [6 empty] | # | [11 empty] | 125 | [16 empty] | 500000
| 'To-Be' Key HRM processes developed and mapped | [6 empty] | # | [11 empty] | 1 | [16 empty] | 300000
| Training on techniques for monitoring overall and institutional-level HRM performance for SHRMD delivered | [6 empty] | # | [11 empty] | 1 | [16 empty] | 50000
Component 2: Efficiency gains in public sector operations and a more cost-effective del of pub servs
| e-Government strategy completed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 396000
| ICT norms and standards produced (cumulative) | [6 empty] | # | [11 empty] | 1 | [16 empty] | 315000
| e-Gov Jamaica training programs delivered (cumulative) | [6 empty] | # | [11 empty] | 9 | [16 empty] | 889000
| GEI business process reengineering completed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 40000
| GEI process automation completed and online applications system in operation | [6 empty] | # | [11 empty] | 1 | [16 empty] | 450000
| GEI training program on the new system delivered (cumulative) | [6 empty] | # | [11 empty] | 1 | [16 empty] | 10000
| Online business registration system in operation | [6 empty] | # | [11 empty] | 1 | [16 empty] | 228000
| Business registration kiosks in operation (cumulative) | [6 empty] | # | [11 empty] | 23 | [16 empty] | 23000
| Business registration seminars and workshops delivered (cumulative) | [6 empty] | # | [11 empty] | 1 | [16 empty] | 10000
| Communications campaign implemented (cumulative) | [6 empty] | # | [11 empty] | 1 | [16 empty] | 39000
| Study Tour completed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 25000
| HRSSC Operating Model designed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 578250
| Technical specification designed and available for HRSSC facility, including ICT infrastructure | [6 empty] | # | [11 empty] | 1 | [16 empty] | 241140
| ICT infrastructure to operate HRSSC in operation | [6 empty] | # | [11 empty] | 1 | [16 empty] | 707610
| Training to HRSSC agents/workers delivered | [6 empty] | # | [11 empty] | 1 | [16 empty] | 48000
Component 3: Control systems and accountability
| Auditors trained - in country - for developing/up-dating PA knowledge and skills | [6 empty] | # | [11 empty] | 90 | [16 empty] | 268000
| Auditors trained  in country and overseas for developing/updating ITA knowledge and skills | [6 empty] | # | [11 empty] | 90 | [16 empty] | 165000
| ITA manual drafted and disseminated | [6 empty] | # | [11 empty] | 1 | [16 empty] | 61000
| Auditors trained overseas completed | [6 empty] | # | [11 empty] | 12 | [16 empty] | 96000
| Additional licenses for interrogation software installed | [6 empty] | # | [11 empty] | 12 | [16 empty] | 75200
| Professional Development framework for Internal Audit Units (IAU) completed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 105000
| Automated internal audit system in operation | [6 empty] | % of IAU | [11 empty] | 100 | [16 empty] | 805400
| Internal Audit Manual updated (unit of measure is 1 manual) | [6 empty] | Manual | [11 empty] | 1 | [16 empty] | 17400
| IA employees trained | [6 empty] | # of Auditors | [11 empty] | 240 | [16 empty] | 152400
| Procurement Manual published, including updated bidding documents | [6 empty] | # | [11 empty] | 1 | [16 empty] | 80000
| Procurement employees trained under new curricula (MIND) (cumulative) | [6 empty] | # | [11 empty] | 1200 | [16 empty] | 450000
| Sensitization and awareness campaign implemented | [6 empty] | # | [11 empty] | 2 | [16 empty] | 80000
| Procurement employees certified (cumulative) | [6 empty] | # | [11 empty] | 200 | [16 empty] | 650000
| E-tendering software at MOFP in operation | [6 empty] | # | [11 empty] | 1 | [16 empty] | 2160000
| Management Accountability Framework designed | [6 empty] | # | [11 empty] | 1 | [16 empty] | 150000
| Technical Office established and functioning | [6 empty] | # | [11 empty] | 1 | [16 empty] | 528000
| Training for PAC and PAAC members delivered | [6 empty] | # | [11 empty] | 4 | [16 empty] | 80000
TOTAL | [36 empty] | 28501935
Correlation to outcomes
- No information available
Performance
Performance Index (PI)
PI x % Disbursed
Earned Value (EV)
Issues
- No information available
Risks
- No information available
Lessons Learned
- No lessons learned have been recorded for this project.