## Sheet1
PROCUREMENT PLAN FOR BANK EXECUTED OPERATIONS
Country: Brazil |  |  | Executing agency: Inter-American Development Bank | [9 empty] | UDR: CBR
Project number: BR-T1377 |  | Title of Project: InfraInvest: Sustainable Infrastructure for Brazil
Period covered by the plan: 24 months |  |  |  |  | Total Project Amount US$: 600,000
Component | Procurement Type | Service type | Description (4) | Estimated contract cost (US$) | Selection Method (2) | Type of contract | Source of financing and percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  | International Competitive Bidding
Component 1 | A. Consulting services: | Firm Consultant (GN-2765) | Develop an economic analysis to identify opportunities that support a greener growth pathway for sustainable infrastructure and to influence planning and the political decision-making process under the NDC implementation in Brazil. | 215000 | SSS | Lump Sum | 215000 | 100 |  |  | 2018-01-01 | 2018-02-01 |  | National Competitive Bidding
Component 2 | A. Consulting services: | Firm Consultant (GN-2765) | Develop an analysis at city level to identify priority areas of investments in sustainable infrastructure and produce recommendations for a package of policy and investments solutions to facilitate its implementation; including the identification of financing challenges and solutions to deliver sustainable infrastructure at city level, with particular focus on PPPs. | 165000 | SSS | Lump Sum | 165000 | 100 |  |  | 2018-01-01 | 2018-02-01 |  | Shopping
Component 2 | A. Consulting services: | Firm Consultant (GN-2765) | Strengthen regulatory frameworks for concessions and PPPs for sustainable infrastructure, including (i) identify the improvements needed on norms and regulations for the delivery effective concessions and PPPs; (ii) access how the public and private sector could address the main challenges faced by cities when elaborating a project, focusing on sustainability aspects, and (iii) work with one city to design and structure a clear pipeline of sustainable infrastructure projects. | 150000 | SC > $100K and <= $250K | Lump Sum | 150000 | 100 |  |  | 2018-01-01 | 2018-02-01 |  | Least-Cost Selection
Component 2 | A. Consulting services: | Firm Consultant (GN-2765) | Sustainable infrastructure PPP pilot project in a medium size municipality. | 50000 | SC <= $100K | Lump Sum | 50000 |  |  |  | 2018-02-01 | 2018-03-01
Component 3 | A. Consulting services: | Firm Consultant (GN-2765) | Structured dialogues between government (national and sub-national), as well as with private financial institutions to develop a joinT agenda to scale up investments of low carbon sustainable infrastructure . | 20000 | SC <= $100K | Lump Sum | 20000 | 100 |  |  | 2018-01-01 | 2018-02-01
Prepared by: Barbara Brakarz |  |  | Total | 600000 |  |  | 600000
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive <= 100K (SC <=100K); Simplified Competitive >100K and <=250K (SC >100K and <=250K); Fully Competitive >250K and Framework Agreement Task Order (FWTO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select comp | Select Proc. Type | select Service type
Component 1 | A. Consulting services: | Individual Consultant (AM-650) | description | amount | select method | Select Cont. Type
Component 2 | B. Goods (2) | Firm Consultant (GN-2765) |  |  | SSS | Lump Sum
Component 3 | C. Non consulting services | Goods Included in Firm Cons. RFP |  |  | IICQ | Framework
Component 4 |  | Corp. Procurement (GN-2303) |  |  | SC <= $100K
Component 5 |  |  |  |  | SC > $100K and <= $250K
FC > $250K
FWTO