- Results Matrix

- Objective: The general objective is to contribute to the reduction in crime and violence (homicides, armed robberies and rapes) in The Bahamas. The specific objectives are to: (i) improve behaviours for non-violent conflict resolution in New Providence; (ii) increase employability and employment of the at-risk youth population in New Providence; (iii) strengthen institutional capabilities of justice services; and (iv) reduce the recidivism rate among those persons within the prison system.

IMPACT

| Indicators | Unit of Measure | Baseline |  | Targets |  | Source/Means of verification | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year | Value | Year |  |  |
| EXPECTED IMPACT: To reduce crime and violence (homicides, armed robberies and rapes) in the Bahamas. |  |  |  |  |  |  |  |
| - Homicide in Bahamas | Rate (# of homicides/ 100,000 inhabitants) | 31.5 | 2013 | 27.19 | 2020 | Royal Bahamas Police Force | The homicide rate was calculated using the number of 2013 reported homicides and the annual population projection by The Bahamas DOS. The rates projection for 2020 takes account of the increasing trend observed over three years and to which the percentage established by evidence (5% and 11%) is added and adjusted by the percentage of the population benefited by the program. |
| - Armed Robbery in Bahamas | Rate (# of armed robberies/ 100,000 inhabitants) | 270.8 | 2013 | 244.4 | 2020 | Royal Bahamas Police Force | Armed Robbery includes robbery/assault with intent to rob, robbery with aggravation, robbery with violence, robbery under arms and larceny from the person. The robbery rate was calculated using the number of 2013 reported robberies and estimated national population projection by DOS. The rates projection for 2020 is calculated by applying a 5% reduction established by the evidence and adjusted by the population benefited by the program. |
| - Rape in Bahamas | Rate (# of rapes/ 100,000 inhabitants) | 27.6 | 2013 | 24.25 | 2020 | Royal Bahamas Police Force | Rape means sexual intercourse without valid consent. The rape rate was calculated using the number of 2013 reported rapes by the RBPF and population estimates from the DOS. The rates projection for 2020 takes account of the increasing trend observed over three years and to which the percentage established by evidence (4% and 15%) is added and adjusted by the percentage of the population benefited by the program. |

EXPECTED OUTCOME

| Indicators | Unit of Measure | Baseline |  |  | Midterm measurements |  |  | Targets |  | Source | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Value | Year |  | Value |  | Year | Value | Year |  |  |
| OUTCOME 1 – Improve behaviors for non-violent conflict resolution in New Providence |  |  |  |  |  |  |  |  |  |  |  |
| - Persons who have been a victim of assaults in the last 12 months in New Providence | % | 6 | 2014 |  |  |  |  | 5 | 2020 | Victimization Survey (LAPOP) | Baseline value corresponds to the 2014 Victimization Survey, (Question number: IVOL5, 5A). There is no midterm target, since the survey will be conducted at the end. |
| - Rape in New Providence | Rate (# of Rapes /100,000 inhabitants) | 34.6 | 2013 |  | 33.1 |  | 2017 | 31.8 | 2020 | Royal Bahamas Police Force | Rates projection for 2020 takes into account the increasing trend observed over three years and to which the percentage established by evidence (4% and 20%) is added and adjusted by the benefited population. |
| - Students who have been in a physical fight one or more times during the past 12 months | % | 40.4 | 2011 |  | 39.7 |  | 2017 | 39.3 | 2020 | The Bahamas Secondary School Drug Prevalence Survey, 2011 | Baseline value corresponds to the 2011 Bahamas Secondary School Drug Survey. The final target is consistent with evidence suggesting a 30% reduction in physical aggression. |
| INTERMEDIARY OUTCOME 1 |  |  |  |  |  |  |  |  |  |  |  |
| - Persons who believes that a man is justified to hits his wife/partner | % | 33 | 2012 |  | 32.8 |  | 2017 | 32.6 | 2020 | COB and Bahamas crisis center survey | Baseline value corresponds to the 2012 Bahamas Healthy Relationships Survey. The final target assumes a conservative impact of 20% reduction consistent with the evidence. |
| - Persons who believe that it is necessary to hit or physically punish a child who misbehave | % | 57.1 | 2014 |  |  |  | 2017 | 54.9 | 2020 | Victimization Survey (LAPOP) | Baseline is estimated based on the 2014 Victimization Survey (Question number: VOL207n). The time period for this indicator refers to the year within which the Survey is conducted. The final target is consistent with evidence suggesting a 22% reduction on coercive parenting techniques. |
| - Students who admitted to caring a weapon such as a gun or knife on school property | % | 10.4 | 2011 |  | 9.9 |  | 2017 | 9.6 | 2020 | The Bahamas Secondary School Drug Prevalence Survey, 2011 | Baseline value corresponds to the 2011 Bahamas Secondary School Drug Survey. The final target is consistent with evidence suggesting a 40% reduction in delinquency. |
| OUTCOME 2 – Increased employability and employment of the at-risk youth population in New Providence and strengthening of the Public Employment Services |  |  |  |  |  |  |  |  |  |  |  |
| - At-risk youth 15-29 certified in the “training for employment” who have a job in the relevant sector 3 months after completing training | % (of at-risk youth 15-29 trained with a job / Total of at-risk youth 15-29 trained) | 30 |  | 2014 |  | 35 | 2017 | 40 | 2019 | Survey | Survey to be carried out 3 months after training to a sample. We would also report yearly, which would allow us to know what areas of training are not working. Baseline value corresponds to the NTA placement rate as reported by them. Targets are consistent with impact evaluations of several employment programs previously financed by the IDB. |
| - Job placement rate by PES in New Providence | Rate (# of placed individuals / # registered individuals) | 2 |  | 2014 |  | 15 | 2017 | 18 | 2020 | PES | Baseline value corresponds to official data from the Bahamas Employment Exchange. Targets are based on an analysis of PES in the region. |
| INTEMEDIARY OUTCOME #2 |  |  |  |  |  |  |  |  |  |  |  |
| At-risk youth 15-29 having obtained a certificate of completion in the “training for employability” program that has transitioned to the “training for employment” program up to 6 months after the training for employability program. | % of at-risk youth 15-29 trained that have transitioned to the “training for employment program”/ Total # of at-risk youth 15-29 trained in the “training for employability” program) | 0 |  | 2014 |  | 35 | 2017 | 35 | 2019 | Survey | Survey to be carried out 6 months after training to a sample. We would also report yearly, which would allow us to know what areas of training are not working. The targets are based on evidence provided by Youth Build using international data. |
| OUTCOME 3 - Reduced length of prosecution for criminal cases in the justice system |  |  |  |  |  |  |  |  |  |  |  |
| - Backlog of criminal cases within the justice system reduced | # | 814 |  | 2011 |  | 757 | 2017 | 656 | 2020 | Court System Records | The backlog includes criminal cases originated since 1996. |
| - Cases completed within a year by the court system | % | 18 |  | 2013 |  | 21 | 2017 | 24 | 2020 | Court System Records | Completed cases are defined as those that reach a verdict, according to the Office of the Attorney General. The target is consistent with evidence suggesting a 15% increase in the clearance rate. |
| OUTCOME 4 – Improve BDOCS effectiveness in reducing offender recidivism at the national level |  |  |  |  |  |  |  |  |  |  |  |
| - Recidivism rate among adult offenders | % | 24 | 2013 |  | 22 |  | 2017 | 20 | 2020 | BDOCS | Adults (18-64) who are convicted more than once are considered recidivist. The target is consistent with evidence suggesting a 25% decrease on recidivism. Even though, this component will also target juveniles within DRWS, this has not been included as a result indicator, given the deficiencies in DRWS data collection practices. The program will support the DRWS in the collection and analysis of data through the implementation of a case management and monitoring system. |
| INTERMEDIARY OUTCOME 4 |  |  |  |  |  |  |  |  |  |  |  |
| - Percentage of inmates who completed the work release program and held a job for at least six months | % | 2 | 2013 |  | 3 |  | 2017 | 3 | 2020 | BDOCS |  |

OUTPUTS

| Output | Estimated Cost (US$) | Unit of measure | Baseline | Year 1 | Annual Cost | Year 2 | Annual Cost | Year 3 | Annual Cost | Year 4 | Annual Cost | Year 5 | Annual Cost | Final Target | Sources |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Social C&V prevention in New Providence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Number of community needs and asset assessments completed. | 290,000 | # of community assessments | 0 | 5 | 145,000 | 5 | 145,000 |  |  |  |  |  |  | 10 | PIU |
| - Number of Community Centers refurbished and expanded. | 2,000,000 | # of Community Centers | 0 |  |  | 5 | 1,000,000 | 5 | 1,000,000 |  |  |  |  | 10 | PIU |
| - Number of Community Leaders trained and certified on community mobilization and gender based violence prevention. | 62,000 | # Community Leaders | 0 | 5 | 9,300 | 5 | 18,600 | 5 | 18,600 | 5 | 15,500 |  |  | 20 | PIU |
| - Number of community members trained and certified on Parenting. | 159,000 | # of community members | 0 | 50 | 15,900 | 150 | 47,700 | 100 | 31,800 | 100 | 31,800 | 100 | 31,800 | 500 | PIU |
| - Number of community members trained and certified on preventing Violence against Women. | 124,000 | # of community members | 0 | 0 |  | 30 | 9,300 | 160 | 49,600 | 160 | 49,600 | 50 | 15,500 | 400 | PIU |
| - Number of surveys on Violence Against Women completed | 760,000 | #of surveys | 0 | 0 |  | 1 | 380,000 |  |  |  |  | 1 | 380,000 | 2 | PIU |
| - Number of community members trained and certified on preventing sexual assault. | 124,000 | # of community members | 0 | 0 |  | 30 | 9,300 | 160 | 49,600 | 160 | 49,600 | 50 | 15,500 | 400 | PIU |
| - Number of comprehensive care model for women who experience sexual violence. | 20,000 | # of models | 0 | 1 | 20,000 |  |  |  |  |  |  |  |  | 1 | PIU |
| - Number of community members trained on conflict resolution. | 120,000 | # of community member | 0 | 0 |  | 30 | 9,000 | 160 | 48,000 | 160 | 48,000 | 50 | 15,000 | 400 | PIU |
| - Number of public awareness campaigns in the media developed and implemented. | 300,000 | # of campaigns | 0 | 0 |  | 1 | 100,000 | 1 | 100,000 | 1 | 100,000 |  |  | 3 | PIU |
| - Number of feasibility studies for violence interruption model completed. | 35,000 | # of studies | 0 |  |  | 1 | 35,000 |  |  |  |  |  |  | 1 | PIU |
| - Number of community violence interrupters trained. | 300,000 | # of interrupters | 0 |  |  |  |  | 30 | 450,000 |  |  |  |  | 30 | PIU |
| - Number of community members trained and certified in mediation and conflict resolution | 90,000 | # of community member | 0 |  |  |  |  | 150 | 25,005 | 150 | 25,005 |  |  | 300 | PIU |
| - Life Skills Training sessions in schools | 217,500 | # of workshops | 0 |  |  | 25 | 72,500 | 20 | 58,000 | 20 | 58,000 | 10 | 29,000 | 75 | PIU |
| - Safe Dates training sessions in schools | 247,500 | # of workshops | 0 |  |  | 25 | 82,500 | 20 | 66,000 | 20 | 66,000 | 10 | 33,000 | 75 | PIU |
| Component 2: Youth employability and employment training and strengthening of the PES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Number of at-risk youth 15-29 that finished their soft skills training (obtaining a certificate of completion) in the “training for employability” program in New Providence | 1,979,555 | # of trained youth | 0 | 0 |  | 500 | 989,776 | 500 | 989,777 | 0 |  | 0 |  | 1000 | piu |
| - Number of surveys for “training for employability program” completed | 20,445 | # of surveys | 0 | 0 |  | 0 |  | 1 | 8,925 |  |  | 1 | 11,500 | 2 | PIU |
| - Number of at-risk youth 15-29 that finished their soft + technical skills training (obtaining a certificate of completion) in the “training for employment” program in New Providence | 1,576,975 | # of trained youth | 0 |  |  | 250 | 246,403 | 550 | 542,085 | 550 | 542,085 | 250 | 246,403 | 1600 | PIU |
| - Number of surveys for “training for employment program” completed | 23,025 | # of surveys | 0 | 0 |  | 0 |  | 1 | 5,425 | 1 | 10,550 | 1 | 7,050 | 1 | PIU |
| - Electronic Labour Exchange enhanced | 120,000 | # of System | 0 |  |  |  |  | 1 | 120,000 |  |  |  |  | 1 | PIU |
| - Number of PES offices improved | 144,000 | # of Offices | 0 | 0 |  | 3 | 144,000 | 0 |  | 0 |  | 0 |  | 3 | PIU |
| - Number of newly registered unemployed in the PES in New Providence | 108,000 | # registered unemployed | 0 | 0 |  | 350 | 15,429 | 700 | 30,857 | 700 | 30,857 | 700 | 30,857 | 2450 | PIU |
| - Number of newly registered vacancies in the PES in New Providence | 108,000 | # registered vacancies | 0 | 0 |  | 200 | 10,800 | 600 | 32,400 | 600 | 32,400 | 600 | 32,400 | 2000 | PIU |
| Component 3: Strengthening of the justice administration system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Case management system and scheduling system designed and implemented | 2,750,000 | # of case management and scheduling systems | 0 | 1 | 250,000 | 3 | 750,000 | 3 | 750,000 | 3 | 750,000 | 1 | 250,000 | 11 | PIU |
| - Court Recording System expanded | 1,260,000 | # of courts | 4 |  |  | 1 | 180,000 | 2 | 360,000 | 2 | 360,000 | 2 | 360,000 | 7 | PIU |
| - Public Defender Programme in operation | 1,214,000 | # of units | 0 |  |  |  |  | 1 | 1,214,000 |  |  |  |  | 1 | PIU |
| - Restorative justice services plan designed and implemented. | 150,800 | # of plans | 0 |  |  | 1 | 150,800 |  |  |  |  |  |  | 1 | PIU |
| - Restorative justice services centers renovated. | 180,000 | # of renovated centers | 0 |  |  |  |  | 1 | 90,000 | 1 | 90,000 |  |  | 2 | PIU |
| Component 4: Rehabilitation and Reintegration of offenders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Number of comprehensive rehabilitation model plans for inmates designed and implemented. | 350,000 | # of models | 0 | 1 | 350,000 |  |  |  |  |  |  |  |  | 1 | PIU |
| - Number of comprehensive rehabilitation model plans for juveniles designed and implemented | 350,000 | # of models | 0 | 1 | 350,000 |  |  |  |  |  |  |  |  | 1 | PIU |
| - Number of inmates trained and certified | 387,500 | # inmates | 0 |  |  | 50 | 32,293 | 150 | 96,875 | 200 | 129,166 | 200 | 129,166 | 600 | PIU |
| - Number of juveniles offenders trained and certified | 387,500 | # of juvenile offenders | 0 |  |  | 50 | 43,050 | 100 | 86,100 | 100 | 86,100 | 200 | 172,200 | 450 | PIU |
| - Number of case management and monitoring systems for inmates designed and implemented. | 425,000 | # of systems | 0 |  |  | 1 | 425,000 |  |  |  |  |  |  | 1 | PIU |
| - Number of case management and monitoring systems for juveniles designed and implemented. | 425,000 | # of systems | 0 |  |  | 1 | 425,000 |  |  |  |  |  |  | 1 | PIU |
| - Number of DOCS staff who completed training in rehabilitation and social integration model. | 202,500 | # of staff | 10 |  |  |  |  | 200 | 67,500 | 200 | 67,500 | 200 | 67,500 | 600 | PIU |
| - Number of DRWS staff who completed training in rehabilitation and social integration model. | 202,500 | # of staff | 0 |  |  |  |  | 40 | 54,000 | 50 | 67,500 | 60 | 81,000 | 150 | PIU |
| - Number of Work Release Programme expanded | 400,000 |  | 1 |  |  | 1 | 400,000 |  |  |  |  |  |  | 1 | PIU |
| - Number of inmates who completed the work release program. | 250,000 | # of inmates | 20 | 0 |  | 10 | 25,000 | 20 | 50,000 | 40 | 100,000 | 30 | 75,000 | 100 | PIU |
| Total estimated costs of outputs |  |  |  |  |  |  |  |  |  |  | US$17,863,800 |  |  |  |  |
| Total estimated costs for Evaluation, Audit, Project Administration, and Contingencies |  |  |  |  |  |  |  |  |  |  | US$2,136,200 |  |  |  |  |
| Total estimated cost of the Programme |  |  |  |  |  |  |  |  |  |  | US$20,000,000 |  |  |  |  |

Garicano and Haeton (2010). 5% reduction (estimating the impact of combined information and investigation improvements on crime reduction). 11% additional impact assumed to be conservative given the interventions proposed and the results achieved in other programs ((Skogan, et al. (2008).  CureViolence model reduced overall homicides in Chicago by 25 % in the intervention year).

Garicano and Haeton (2010). 5% reduction (estimating the impact of combined information and investigation improvements on crime reduction).

Hanson & Broom (2005). 4%  reduction of sexual assaults,  and a 20% additional impact on sexual violence assumed to be conservative given the intervention proposed and the results achieved in other programs (Foshee et al. 1998. Safe Dates reduced 60% less sexual violence perpetration).

Garicano and Haeton (2010). The final target is consistent with evidence suggesting a 5% reduction of crime (estimating the impact of combined information and investigation improvements on crime reduction).

Hanson & Broom (2005). 4%  reduction of sexual assaults through risk reduction programs and a 20% additional impact on sexual violence assumed to be conservative given the intervention proposed and the results achieved in other programs (Foshee et al. 1998. Safe Dates program reduced 60% less sexual violence perpetration).

Botvin, G. et al (2006), the Life Skills Training program  found stronger effects were in the group of students who received at least half of the intervention compared with controls, which included less physical aggression (30%).

Foshee et al. (1998). Safe Dates program reduced 60% less in violence perpetrated against a current dating partner. A 20% decrease was assumed to be conservative given the intervention proposed and the results achieved in other programs.

Morawska, A. et al. 2010. The Triple P program found a 22% reduction in a validated scale measuring parental over-reactivity. As limited documented experience for this intervention in developing countries is available,a conservative target of 11% decrease in coercive parenting.

Botvin, G. et al (2006), the Life Skills Training program  found stronger effects were in the group of students who received at least half of the intervention compared with controls, which included less delinquency (40%).

González-Velosa, C., L. Ripani and D. Rosas Shady (2012). “How Can Job Opportunities for Young People in Latin America be Improved?”, IDB Publications 78338, Inter-American Development Bank.

Information from questionnaire distributed to members of the Employment Services Network in Latin America and the Caribbean (RED SEALC).

See case study on YouthBuild in Hoffman, Joan Serra, Lyndee Knox, and Robert Cohen, eds. (2011) Beyond Suppression: Global Perspectives on Youth Violence. Praeger Press

The backlog includes criminal cases originated since 1996. Evidence from a pilot project in 8 courts of India, show a 7% average rate of decrease of old backlog, when combining training of staff with case management systems (Salkute, S, 2014).

Garicano,. & Heaton (2010),  reforms integrating technology and technical capacity found to produce a relative increase of 15% in the clearance rate.

Lipsey, M. W., & Cullen, F. T. (2007). Evidence indicate that adult rehabilitation programs based on cognitive behavioral therapies, have shown a fall in recidivism by 25% in the targeted population. As limited documented experience for this intervention in developing countries is available, a conservative target of a 12% decrease in adult recidivism is set.

Soft skills to prevent violent behavior and substance abuse in schools.

Interruptions to prevent the initiation of emotional, physical and sexual abuse on dates or in-between individuals in a dating relationship.

Training for employability is a labor market intervention designed for those more at risk. It includes training and labour market experience, the development of a series of competencies in the areas of logical thinking, effective communication and self-esteem. Training for employment targets more job-ready youth with the objective of inserting them in an open vacancy in the productive sector.