Summary of results and lessons learned from Citizen Security Programs in the Caribbean

The Citizen Security and Justice Program (CSJP) will contribute to reducing C&V in The Bahamas, through a comprehensive approach that combines preventive strategies with institutional strengthening activities both at the national and local levels. It seeks to support the implementation of interventions that address the most modifiable risk factors, and promote community mobilization and local social development interventions in high crime, disadvantaged, low-income urban neighborhoods. Indeed, the programme will emphasize: (i) social prevention in New Providence island (where the incidence of C&V is most acutely felt) and (ii) strengthening institutional capacity within agencies responsible for the prosecution, sentencing and rehabilitation of persons in conflict with the law.

The CSJP is the first citizen security project in The Bahamas and it is consistent with previous Bank experience in the Caribbean where similar multi-sector strategies and evidence-based interventions have been implemented, for example in Guyana (GY0071), Jamaica (JA105; JA-L1009) and Trinidad and Tobago (TT-L1003). The project completion reports of the closed projects suggest the following results:

- Citizen Security Programme in Guyana (GY0071)

Approved in 2006, the Citizen Security Programme in Guyana aimed to “enhance citizen security and coexistence by contributing to the reduction in levels of crime, violence and insecurity in Guyana.”

CSP formally closed in June 2014. Using survey data and project monitoring data collected under the project, an initial assessment of the indicators as at project end was conducted by an independent consultant in March 2014. The assessment found that all expected outputs had been achieved, either wholly or in part.  In certain cases, the level of output achievement vastly exceeded the levels anticipated at project start.  An important example of this is the development of the Integrated Crime Information System, which was expected to be implemented in 18 Police stations but was implemented in 39 police stations by project end.

As such, there is insufficient data at this time to determine the project’s results in the intervention zones or to demonstrate causation between reported outcomes and project interventions. Nevertheless, as CSP selected intervention communities based on severity of crime levels at the time of project design (among other criteria), it is possible that any regional trend direction would have been influenced in its direction by similar trends occurring in the intervention communities.  This will be examined in greater depth in the ex-post evaluation.

- Citizen Security and Justice Programme in Jamaica (JA105; JA-L1009)

The IDB has supported the Government of Jamaica with the citizen security and justice programs (CSJP) since 2001, Jamaica I (2001-2009) and II (2009-present) had a community-based focus, beginning with 9 communities and expanding to 28 and then to 50 in the second phase. Interventions in the first phase consisted mainly of remedial education, life skills, parenting, and vocational training delivered by nongovernmental organizations (NGOs); and those in the second phase shifted to scholarship and internship programs for inner-city students at the secondary and tertiary levels, maintaining previous community activities, but increasingly providing them through community-based organizations (CBOs). In addition, both projects worked with the criminal justice system to improve criminal investigation, create restorative justice tribunals, create a system for facilitating information-sharing among institutions, and provide police with training in community policing.

In 2014, IDB approved an additional USD$55 million program CSJP III (JA-L1043), which included a £10 million grant provided by the UK’s Department for International Development (DFID) and a CAN$20 million grant from the Department of Foreign Affairs, Trade and Development of Canada (DFATD).  CSJP’s focus has been on improving behaviors for non-violent conflict resolution, increasing jobs and employability of youth, and increasing access to effective community and alternative justice services.

According to OVE’s evaluation, “The Implementation Challenge: Lessons From Five Citizen Security Projects” (RE-456), the CSJP I exceeded its target objectives in terms of reduction of homicides and major violent crimes in targeted communities. Specific elements of the design contributed to produce the intended results, for instance the interventions financed by the projects were consistent with available evidence and specialized literature: parenting, recreational activities, remedial education, vocational training, community organization, community.

This initial assessment provided the initial draft of CSP’s Project Completion Report, which may be found here.