## Sheet1
Project: OECS Trade Capacity Building
Project Number RG-T1427
Period comprised in this Procurement Plan: From January 2009 to December 2010
Ref. No. | Description of and category of procurement contract | Estimated cost in Canadian dollars | Procure-ment method 1 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
1 | GOODS
1.1 | Component I Air tickets | 7600 | PC | N/A | 100% |  | No | Sem II 2009 | Sem IV 2009
1.2 | Component III Air Tickets (approx. 15) | 9500 | PC | N/A | 100% |  | No | Sem III 2009 | Sem IV 2009
1.3 | Component III Logistics (venue, equipment, communications) | 3000 | PC | N/A | 100% |  | No | Sem III 2009 | Sem IV 2009
1.4 | Component IV Air tickets (approx. 25-30) | 21500 | PC | N/A | 100% |  | No | Sem IV 2009 | Sem II 2010
1.5 | Component IV Accomodation (approx. 25-30) | 22700 | PC | N/A | 100% |  | No | Sem IV 2009 | Sem II 2010
1.6 | Component IV Logistics (venue, equipment, communications) | 4000 | PC | N/A | 100% |  | No | Sem IV 2009 | Sem II 2010
1.7 | Component V Air tickets (approx. 10) | 6300 | PC | N/A | 100% |  | No | Sem IV 2009 | Sem II 2010
1.8 | Component V Logistics (venue, equipment, communications) | 1300 | PC | N/A | 100% |  | No | Sem IV 2009 | Sem II 2010
WORKS
N/A
Non-consulting services
N/A
Ref. No. | Description of and category of procurement contract | Estimated cost in Canadian dollars | Procure-ment method 1 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication (Yes/No) | Estimated Dates |  | Status (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
2 | CONSULTING SERVICES
2.1 | Component I Contracting of 1 individual consultant for the design of a market intelligence system | 14900 | QCII | Ex-ante | 100% |  | No | Sem II 2009 | Sem IV 2009
2.2 | Component I Contracting of 1 individual consultant to assist with the design of a market intelligence system | 4000 | QCNI | Ex-ante | 100% |  | No | Sem II 2009 | Sem IV 2009
2.3 | Component II Contracting of 3 individual consultants for technical studies to inform the participation of the OECS in future trade negotiations. | 76000 | QCII | Ex-ante | 100% |  | No | Sem II 2009 | Sem II 2010
2.4 | Component VI Contracting of 1 individual consultant to prepare an institutional assessment and strategic plan and to support project execution. | 96000 | QCNI | Ex-ante | 100% |  | No | Sem I 2009 | Sem IV 2010
1 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.