## Sheet1
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: Regional | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: IFD/CMF
Project number: RG-T3368 |  |  |  |  | Project name: Regional Green Bonds Program for Latin America and the Caribbean
Period covered by the Plan: [60 months] |  |  |  |  | Total Project Amount: |  | 1900000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
|  |  | Activity/Component 1: Support to NDBs in the issuing of pilot green or sustainable bond programs | [11 empty] | International Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultancies (7) to determine eligible loan sub-portfolios susceptible to be securitized | 245000 | ICQ | Lump Sum | 245000 | 100% | 0 | 0% | Q1 | 2019-02-28 | 3 months | Retainer to be considered | National Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultancies (4) to study financial viability of project and/or design credit enhancement mechanism for bond | 330000 | ICQ | Lump Sum | 330000 | 100% |  |  | Q2 | 2019-04-01 | 3 months |  | Shopping
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy services (5) for second party review of eligible bond portfolio - Including travel expenses | 125000 | SSS | Lump Sum | 125000 | 100% |  |  | Q3 | 2019-04-01 | 3 months | Retainer to be considered | Least-Cost Selection
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Promotion and logistics services related to issuance roadshow and promotion (including regional) | 50000 | SSS | Lump Sum | 50000 | 100% |  |  | Q2 | 2019-06-01 | 3 months |  | Quality Based Selection
|  |  | Activity/Component 2: Support to government entities at national and sub-national level |  |  |  |  | 100% | [6 empty] | Quality and Cost Based Selection
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultancies (5) to identify opportunity and develop framework | 250000 | ICQ | Lump Sum | 250000 | 100% | 0 | 0% | Q1 | 2019-02-28 | 3 months | Retainer to be considered | National Competitive Bidding
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Consultancies (5) to study financial viability of project and/or design credit enhancement mechanism for bond | 400000 | ICQ | Lump Sum | 400000 | 100% |  |  | Q2 | 2019-04-01 | 3 months |  | Shopping
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy for the structuring of a regional financial mechanim to aggregate and support bond issuance | 200000 | SCS | Lump Sum | 200000 | 100% |  |  | Q2 | 2019-04-01 | 6 months
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy services (5) for second party review of eligible bond portfolio - Including travel expenses | 125000 | SSS | Lump Sum | 125000 | 100% |  |  | Q3 | 2019-04-01 | 3 months | Retainer to be considered | Least-Cost Selection
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Promotion and logistics services related to issuance roadshow and promotion (including regional event) | 75000 | SSS | Lump Sum | 75000 | 100% |  |  | Q2 | 2019-06-01 | 3 months |  | Quality Based Selection
|  |  | Activity 3: development of knowledge products |  |  |  |  | 100% | [6 empty] | Selection under a Fixed Budget
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy firm to develop knowledge products and support web platform content | 15000 | SSS | Lump Sum | 15000 | 100% |  |  | Q1 | 2019-02-15
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy firm to support web platform (IT related activities) including hosting and server costs. | 15000 | SSS | Lump Sum | 15000 | 100% |  |  | Q1 | 2019-02-15
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | 1 Regional event to promote lessons learned and opportunities for NDBs. | 20000 |  | Lump Sum | 20000 | 100%
Component 4 |  |  | Activity 4: Survey and study activities |  |  |  |  | 100%
Component 4 | A. Consulting services | Consulting Firm (GN-2765) | Consultancy services to provide design, realization and analysis of survey | 25000 |  |  | 25000 | 100% |  |  | Q3 | 2019-02-28 | 60 months
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | 1 Regional event to promote survey results | 25000 |  | Lump Sum | 25000 | 100% |  |  | Contingent | Contingent
Prepared by: | Maria Netto (IFD/CMF) |  | TOTALS | 1900000 |  |  | 1900000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
170000
0.089474
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | ICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO
Component 6
Component 7
Component 8
Other