**Procurement Plan**

Project CH-T1151

Executing agency: BID

Date: 2014

| **Component / Activity** | **Service** | **Estimated cost**  **(US$)** | | **Procurement Method** | **Prequalification**  **YES/NO** | **Date** | |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **BID** | **Local** |
| **Start** | **End** |
| **Component I: Institutional Framework** |  |  |  |  |  |  |  |
| Strategic Selectivity Study | International Individual Consultants | 80,000 | 0 | IICQ |  | January 2015 | December 2015 |
| Strategic Selectivity Study | National Individual Consultant | 0 | 30,000 | ICQ |  | January 2015 | December 2015 |
| Institutional Regional Review Study | International Firm Consultants | 100,000 | 0 | CQS |  | January 2015 | December 2015 |
| IPR for Development | International Individual Consultants | 50,000 | 0 | IICQ |  | April 2015 | April 2016 |
| IPR for Development – National Workshop | Non consulting services | 0 | 10,000 | PC |  | March 2016 | April 2016 |
|  |  |  |  |  |  |  |  |
| **Component II. Redesign of Public Support Programs** |  |  |  |  |  |  |  |
| Best practices for assessment of RI | International Firm Consultant | 70,000 | 0 | CQS |  | March 2015 | December 2015 |
| Best Practices for assessment of RI – National Workshop.) | Non consulting services | 0 | 10,000 | PC |  | November 2014 | December 2015 |
| Technology Finance Guarantees | International Firm Consultant | 65,000 | 0 | CQS |  | January 2015 | July 2015 |
| Reimbursable Grants Models | International Individual Consultants | 30,000 | 0 | IICQ |  | January 2015 | July 2015 |
| **Coordination** |  |  |  |  |  |  |  |
| Audit and Evaluation | National Individual Consultant | 5,000 | 0 | ICQ |  | TBD | TBD |

ICQ: Individual Consultant Selection Based on Qualifications

IICQ: International Individual Consultant Selection Based on Qualifications

CQS: Selection Based on the Consultants' Qualifications

PC: Price comparison